## Project Charter
Agile Project Charter
General Project Information
Project Name | Organic Product Online Stores
Project Champion | Complete Web system and send EDI request to logistic and manufacturer team
Project Sponsor | HK Organic Food Company
Project Manager | Philip Hui
Stakeholders | Logistic Team, Manufacturer Team, Online Retailer Team
Expected Start Date | 1 Mar, 2019
Expected Completion Date | 3 Apr, 2019
Project Details
Mission | Our mission is to create a web service which can let consumer to purchase organic food. Each teams also will have their own systems. And all systems will be combined into a one system to assist the business operation in the future.
Scope | The Online Retailer Team responsed the development of the online shop website. And the back-end database system responsed the communications betweens the consumer and our inventory. Build-up file transactions and export EDI files with manufacturer team and logistic team
Success Metrics | Consumer can finish the trading and purchase process by using our website. And the inventory system can react well. Also, the system of Logistic and Manufacturer Team also can react with the order operations of retailer system to perform the related actions such as getting cargo from the warehouse and delivering.

## Product Roadmap
Agile Product Roadmap
<Agile Development Project> | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
| 2019-03-01 | 2019-03-08 | 2019-03-15 | 2019-03-22 | 2019-03-29 | 2019-04-05
Online Retailer
Create an Agile Product Roadmap in Smartsheet
Product 1

## Project Plan
Agile Project Plan
Project Name | Organic food online store project
Project Manager | Philip Hui
Project Deliverable | Web System, send EDI request to logistic team and manufacturer team success
Scope Statement | Consumer can finish the trading and purchase process by using our website. And the inventory system can react well
Start Date | 1 Mar, 2019
End Date | 1 Apr, 2019
Overall Progress | Finished Sprint 2 cycle
Smart Sheet Link
Task Name |  | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Organic food online store project |  | 37d | 2019-02-08 | 2019-04-01
Sprint 1 |  | 21d | 2019-02-08 | 2019-03-08
Sprint Planning |  | 6d | 2019-02-08 | 2019-02-15 | Mgr 1, Dev 1, Dev 2 | Philip Hui |  | Complete
Setup staging environment |  | 4d | 2019-02-15 | 2019-02-20 | Dev 1 | Winko |  | Complete
Configure multilingual features |  | 14d | 2019-02-19 | 2019-03-08 | Dev 2 | Kevin |  | Complete
User login function |  | 4d | 2019-03-01 | 2019-03-06 | Dev 2 | Kevin |  | Complete
Product categories |  | 4d | 2019-03-01 | 2019-03-06 | Dev 2 | Kevin |  | Complete
Export CSV files from Database |  | 4d | 2019-03-01 | 2019-03-06 | Dev 1 | Winko |  | Complete
Export JsonString files from Database |  | 4d | 2019-03-01 | 2019-03-06 | Dev 1 | Winko |  | Complete
Testing |  | 7d | 2019-02-27 | 2019-03-07 | QA 1 | Vincent |  | Complete
Fix Period |  | 1d | 2019-03-07 | 2019-03-07 | Dev 1, Dev 2 | Winko |  | Complete
Deploy |  | 1d | 2019-03-08 | 2019-03-08 | Mgr 1, Dev 1, Dev 2 | Harris |  | Complete
Sprint 2 |  | 17d | 2019-03-09 | 2019-04-01
Sprint Planning |  | 4d | 2019-03-09 | 2019-03-13 | Mgr 1, Dev 2 | Philip Hui |  | Complete
Cart function |  | 4d | 2019-03-19 | 2019-03-22 | Dev 2 | Kevin |  | Complete
Payment function |  | 2d | 2019-03-12 | 2019-03-13 | Dev 1 | Winko |  | Complete
Order confirm function (For commerce team) |  | 2d | 2019-03-14 | 2019-03-15 | Dev 1 | Winko |  | Complete
Inventory Management function |  | 4d | 2019-03-18 | 2019-03-21 | Dev 1 | Winko |  | Complete
Testing |  | 3d | 2019-03-22 | 2019-03-26 | QA 1 | Vincent |  | Complete
Fix Period |  | 3d | 2019-03-27 | 2019-03-29 | Dev 1, Dev 2 | Kevin |  | Complete
Deploy |  | 1d | 2019-04-03 | 2019-04-03 | Mgr 1, Dev 1, Dev 2 | Harris |  | Complete

## Product Backlog
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Completed | 5 | Yes
Export csv file for logistic team | Yes | Yes | High | Completed | 1 | Yes
Export json file for manufacturer team | Yes | Yes | High | Completed | 2 | Yes
User login function | Yes | Yes | Low | Completed | 1 | Yes
Product categories | Yes | Yes | Low | Completed | 1 | Yes
Sprint 2 | Yes | Yes | Medium | Completed | 7 | No
Cart function | Yes | Yes | Medium | Completed | 1 | Yes
Payment function | Yes | Yes | Medium | Completed | 3 | Yes
Order confirm function (For commerce team) | Yes | Yes | Medium | Completed | 1 | Yes
Inventory Management function | Yes | Yes | Medium | Completed | 2 | Yes

## User Story
Agile User Story
Feature | User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | 1 | Customer | Enter the related username and password | Enter webstore to buying products
1 | 2 | Customer | View the products on product pages by catrgories | Select the product I want
1 | 3 | Cusstomer | Looking for more products that want to purchase at the same time | Put the items that need to purchase process
1 | 4 | Customer | Finish viewing and ready for confirm the order | Double check the items in shopping cart
1 | 5 | Customer | Pay the order | Get the products
2 | 6 | Commerce Team | Confirm the order has been paid | Confirm user order success and schedule shiping date
2 | 7 | Commerce Team | Check the inventory of each products | Make decision for filling products
2 | 8 | Commerce Team | Send EDI request to manufacturer | Get products from manufacturer
2 | 9 | Commerce Team | Send EDI request to logistics | Delivery products to customers
3 | 10 | Clerical Team | Insert Order Record with standard EDI format into Database | Send EDI to logistic or manufacturer team
4 | 11 | Manager | Enter Management Website | Check the sales report
Case Scenario
Scenario 1: Order product from Manufacturer |  |  | Scenario 2: Delivery product through Logistic to customer
Given I have <qty_of_currentItem> on inventory |  |  | Given I have <qty_of_currentItem> on inventory
When I request <no_of_item_needed> from manufacturer |  |  | When I request <no_of_delivery_item> to logistic
And manufacturer send product (item) to retailer shop |  |  | And Logistic take out product (item) from retailer shop
Then I get new balance <updated_item_qty> on inventory |  |  | Then I get new balance <updated_item_qty> on inventory
¦qty_of_currentItem¦no_of_item_needed¦updated_item_qty¦ |  |  | ¦qty_of_current_item¦no_of_dalivery_item¦updated_item_qty¦
¦0¦100¦100¦ |  |  | ¦100¦50¦50¦
¦100¦50¦150¦ |  |  | ¦200¦150¦50¦

## Sprint Backlog (Backup) (hidden)
Sprint Backlog Template ( Remaining outstanding efforts in hours )
Sprint Number | 1
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 | 8
Task (Design/Development/Task) |  |  |  | 7 | 5 | 3 | 2 | 2 | 2 | 2
Task (Design/Development/Task) |  |  |  | 3 | 2 | 2 | 1 | 1 | 1 | 0
Task (Design/Development/Task) |  |  |  | 4 | 3 | 2 | 2 | 2 | 2 | 2
Task (Design/Development/Task) |  |  |  | 9 | 7 | 5 | 3 | 3 | 1 | 0
User Story #2 | 1
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
User Story #3 | 5
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
User Story #4 | 8
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
User Story #5 | 3
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
Task (Design/Development/Task)
Total |  |  |  | 23 | 17 | 12 | 8 | 8 | 6 | 4
S

## Agile Sprint Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | Day 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Sprint 1
Export CSV file for logistic team | 1 | Winko Lui | Released | 8 | 0.5 | 0.5 | 1 |  |  | 1
Export JSON file for manufacturer team | 2 | Winko Lui | Released | 8 | 2 | 1 | 2 |  |  | 2
User login function | 1 | Kevin Lau | Released | 4 | 1 | 1 | 2 |  |  | 1
Product categories | 1 | Kevin Lau | Released | 4 | 1 | 2 | 1 | 1 |  | 1
Sprint 2
Cart function | 1 | Kevin Lau | Released | 8 | 1 | 1 | 1 | 1 | 2 | 1
Payment function | 3 | Winko Lui | Released | 4 | 1 | 1 | 1 | 1 |  | 2
Order confirm function (For commerce team) | 1 | Winko Lui | Released | 4 | 1 | 0.5 | 1 |  |  | 1
Inventory management function | 2 | Winko Lui | Released | 8 | 1 | 1 | 1 | 1 |  | 1
TOTAL |  |  |  | 48 | 8.5 | 8 | 10 | 4 | 2 | 10

## Sprint Backlog (hidden)
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day Used | Sprint Review
User login function | 1 | Kevin | Released | 2 | 2 | 1
Product categories | 1 | Kevin | Released | 2 | 3 | 1
Cart function |  | Kevin | On going
Cart review function |  | Kevin | On going
Payment system |  | Kevin | On going
Order confirm function (For commerce team) |  | Winko | On going
Inventory management system |  | Winko | On going
EDI Request generator (To manufacturer) | 1 | WInko | Released | 4 | 2 | 1
EDI Request generator (To logistic) | 1 | Winko | Released | 4 | 2 | 1

## Test Plan
Agile Test Plan
Project Name | Organic Product Online Stores |  | Browser: | Philip
Test Case ID | 20190331 |  | Version: | PROD v1.0
Written By: | Vincent |  | Description: | Web Online Store and EDI System
Tested By: | Vincent |  | Tested On: | 2019-03-30
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2019-03-30 | Send edi request to manufacturer if necessarary | Manufacturer is able to receive EDI request | No Issue | Pass
2 | 2019-04-01 | Send edi request to logistics company | Losgistics company is able to receive EDI request | No Issue | Pass
3 | 2019-04-01 | Create a user register page and interface | A register page is shown able to register a user | User is now able to register at the page created. | Pass
4 | 2019-04-01 | Createa a login page and interface | A login page and interface is shown and can be signed in | A working login page has been established. | Pass
6 | 2019-04-01 | Showing the product and divide them into category | Able to view products in category | The products can be viewed with sorted orders, such as name, price, rating and model. | Pass
7 | 2019-04-01 | Create a shopping cart function | Able to put items in shopping cart while view the products at the same time | Shopping cart is now able to store items. | Pass
8 | 2019-04-01 | Create an checkout page | Able to double check items in cart and checkout | Checkout page now is able to show items in shopping cart and provide checkout information like discount and tax. | Pass
9 | 2019-04-01 | create an payment page | Able to pass the payment and check whether order is sucecssfully transfered |  | Fail
10 | 2019-04-01 | Send invoice automatically to user | Able to send invoice to users after an order is made |  | Fail
11 | 2019-04-01 | Check the inventory of each products | Able to distinguish and check whether there is a need to restock | No Issue | Pass

## Release Plan
Agile Release Plan
Sprint | Task | Start | End | Duration | Status | Release Date | Goal
1 | Export csv file for logistic team | 26/2/2019 | 27/2/2019 | 2 | Released | 7/3/2019 | Get products from manufacturer
1 | Export json file for manufacturer team | 28/2/2019 | 1/3/2019 | 2 | Released | 7/3/2019 | Delivery products to customers
1 | User login function | 2/3/2019 | 3/3/2019 | 2 | Released | 2019-07-03 | Enter webstore to buying products
1 | Product categories | 4/3/2019 | 6/3/2019 | 3 | Released | 2019-07-03 | Select the product that user want
2 | Opencart Webpage Update (Web Layout) | 2019-03-15 | 2019-03-17 | 2 | Released | 2019-03-18 | Get the products
2 | Opencart Webpage Update (Purchase Function) | 2019-03-20 | 2019-03-22 | 2 | Released | 2019-03-23 | Put the items that need to purchase process
2 | Opencart Webpage Update (Inventory Checking) | 2019-03-25 | 2019-03-28 | 3 | Released | 2019-03-29 | Double check the items in shopping cart
2 | Sprint backlog update | 2019-03-26 | 2019-03-28 | 2 | Released | 2019-03-29 | deliver a usable product Increment
2 | Product backlog update | 2019-03-29 | 2019-04-01 | 3 | Released | 2019-04-01 | list of all things that needs to be done within the project
2 | Project Plan Update | 2019-03-15 | 2019-03-22 | 7 | Released | 2019-03-23 | A clear procedures and planning of the project
2 | User Story Update | 2019-03-22 | 2019-03-25 | 3 | Released | 2019-03-26 | Clearfy the function performance to achieve the goal
2 | Test Plan Update | 2019-04-01 | 2019-04-02 | 1 | Released | 2019-04-03
2 | Test Online Retailer Store Purechase Function | 2019-04-02 | 2019-04-03 | 1 | Released | 2019-04-03
2 | Release Plan Update | 2019-03-30 | 2019-04-01 | 2 | Released | 2019-04-03
2 | Test Result | 2019-04-02 | 2019-04-03 | 1 | Released | 2019-04-03
2 | Presentation Powerpoint | 2019-03-28 | 2019-03-29 | 1 | Released | 2019-03-29 | Delivery Project demonstration material
0
0
0
0